## Worklog_Tasks&Times
Date | Status | Task | Description/Planning | Task Type | Most suited ILO | Est Hours | Actual Hours | Diff | Evidence link | Task reflection / notes
RETAKE
Week 1
week plan: | Complete the courses; Further expand my knowledge of python in relation to data management and manipulation
Known Risks | Friends are visiting
2023-11-20 | Done | Max 4 hours tasks | Setting up the IDE environment | Programming | ILO 4.2 | 3 | 3 | 0 |  | Already had the libraries installed because of the DuckieTown Challenge.
2023-11-20 | Done | Max 4 hours tasks | PEP 8 Python Style guide | Research | ILO 4.1 | 0.25 | 0.25 | 0 |  | Learned conventions regarding the PEP 8 style guide (mostly about variables and object naming).
2023-11-20 | Done | Max 4 hours tasks | Video: Reproductibility in Data Science | Lecture | ILO 4.2 | 0.5 | 0.5 | 0 |  | Learned more about the process and importance of cleaning data before the visualisation part of the model.
2023-11-20 | Done | Max 4 hours tasks | Video : Testing for Data Scientists | Lecture | ILO 4.2 | 0.66 | 0.66 | 0 |  | Learned about the importance of unit testing, what it entails, and how it helps the people who use your code.
2023-11-20 | Done | Max 4 hours tasks | DataCamp: Unit Testing in python (First part) | Programming | ILO 4.2 | 4 | 3 | -1 | LINK
2023-11-21 | Done | Max 4 hours tasks | Kick-Off | Meeting | ILO 1.4 | 2 | 2 | 0
2023-11-21 | Done | Max 4 hours tasks | Introduction to MetaData | Research | ILO 5.1 | 0.5 | 0.5 | 0 | LINK | Learned about metadata and the data that we will be working with (football player data).
2023-11-21 | Done | Max 4 hours tasks | DataCamp: Data manipulation with pandas | Programming | ILO 4.2 | 4 | 4 | 0 | LINK
2023-11-22 | Done | Max 4 hours tasks | Meditated | Break | ILO 2.5 | 1 | 1 | - | - | Worked towards achieving my SMARTER goals.
2023-11-22 | Done | Max 4 hours tasks | Building the MetaData | Programming | ILO 4.2 | 2 | 2 | 0
2023-11-22 | Done | Max 4 hours tasks | File formats and Pandas | Research | ILO 4.2 | 2 | 2 | 0 |  | Learned about different file formats (CSV, JSON), and the serialisation and deserialisation process of Python objects using the Pickle module
2023-11-22 | Done | Max 4 hours tasks | DataCamp: Introduction to importing data in Python | Programming | ILO 4.1 | 2 | 3 | 1 | LINK
2023-11-23 | Done | Max 4 hours tasks | Directories and its importance | Programming | ILO 4.1 | 1 | 1 | 0
2023-11-23 | Done | Max 4 hours tasks | Introduction to NumPy | Programming | ILO 4.2 | 1 | 1 | 0 | LINK | Understood the NumPy library and its usage better
2023-11-23 | Done | Max 4 hours tasks | Introduction to linear algebra | Study | ILO 7.0 | 2 | 2 | 0 |  | Learned matrices, scalars and vectors, different properties, as well as operations
2023-11-23 | Done | Max 4 hours tasks | Reading: 'The subtle art of not giving' a f*ck by Mark Manson | Study | ILO 2.5 | 4 | 4 | 0 |  | Worked towards achieving my SMARTER goals.
2023-11-23 | Done | Max 4 hours tasks | Reading: linear algebra | Study | ILO 7.0 | 1 | 1 | 0 |  | Learned and revised some basics of algebra.
2023-11-23 | Done | Max 4 hours tasks | Reading: Introduction to NumPy | Study | ILO 7.0 | 0.75 | 1.5 | 0.75 | LINK | Further comprehension into the NumPy library
2023-11-24 | Done | Max 4 hours tasks | RIMV Cleansing | Programming | ILO 4.2 | 2 | 2.5 | 0.5 | LINK
2023-11-24 | Done | Max 4 hours tasks | Titanic Cleansing | Programming | ILO 4.2 | 2 | 2 | 0 | LINK
2023-11-24 | Done | Max 4 hours tasks | Unit Testing | Programming | ILO 4.2 | 2 | 1.5 | -0.5 | LINK
2023-11-24 | Done | Max 4 hours tasks | Integration challenge | Programming | ILO 4.2 | 1.5 | 2 | 0.5 | LINK
|  |  |  | Total Hours |  | 39.16 | 40.41 | 1.25
Week 2
week plan: | Do the readings; get help for pandas; delve deeper into machine learning; concentrate on SMARTER goals
Known Risks | Got sick
2023-11-27 | Done | Max 4 hours tasks | Introduction to ethics | Research | ILO 3.1 | 1 | 1 | 0 | LINK | Learned about the use of ethics in the business world, as well as its importance in the field of AI.
2023-11-27 | Done | Max 4 hours tasks | Reading: 'The subtle art of not giving' a f*ck by Mark Manson | Study | ILO 2.5 | 4 | 4 | 0 |  | Worked towards achieving my SMARTER goals.
2023-11-27 | Done | Max 4 hours tasks | Reading: Chapters 3 & 4 (Dignum, 2019) | Research | ILO 3.1 | 1 | 3 | 2 |  | Learned about ethic in artificial intelligence.
2023-11-28 | Done | Max 4 hours tasks | Critical thinking and reasoning | Research | ILO 6.0 | 1 | 0.75 | -0.25 |  | Learned about different types of reasoning (Induction and Abduction).
2023-11-28 | Done | Max 4 hours tasks | Topics for the dialogue | Research | ILO 6.0 | 1 | 2 | 1
2023-11-28 | Done | Max 4 hours tasks | Lunch break | Break | ILO 1.4 | 1 | 1 | 0 | - | -
2023-11-28 | Done | Max 4 hours tasks | NAC ethics research | Research | ILO 6.0 | 2 | 4 | 2 |  | Researched the ethics side of NAC.
2023-11-28 | Done | Max 4 hours tasks | Reading: 'Naked Statistics' by Charles Wheelan | Study | ILO 2.5 | 1 | 1 | 0 |  | Worked towards achieving my SMARTER goals.
2023-11-29 | Done | Max 4 hours tasks | Writing style | Research | ILO 6.0 | 1 | 1 | 0 |  | Learned about rules of writing and how to avoid writing informally.
2023-11-29 | Done | Max 4 hours tasks | Bias-free language | Research | ILO 6.0 | 0.5 | 1 | 0.5 |  | Learned how to avoid being biased in my writing style.
2023-11-29 | Done | Max 4 hours tasks | Reading: 'Naked Statistics' by Charles Wheelan | Study | ILO 2.5 | 4 | 3 | -1 |  | Worked towards achieving my SMARTER goals.
2023-11-29 | Done | Max 4 hours tasks | Homework | Testing | ILO 6.0 | 0.25 | 0.25 | 0 | LINK | Wrote a title page for the final report.
2023-11-29 | Done | Max 4 hours tasks | Citation | Research | ILO 6.0 | 1 | 2 | 1 |  | Learned about proper APA refrencing (in-text, as well as in-list).
2023-11-30 | Done | Max 4 hours tasks | Citation exercise | Research | ILO 6.0 | 1 | 1 | 0 | LINK
2023-11-30 | Done | Max 4 hours tasks | Research into Python well-known algorithms. | Research | ILO 2.5 | 2 | 2.5 | 0.5 |  | Worked towards achieving my SMARTER goals.
2023-11-30 | Done | Max 4 hours tasks | Reading: 'The subtle art of not giving' a f*ck by Mark Manson | Study | ILO 2.5 | 2 | 2 | 0 |  | Worked towards achieving my SMARTER goals.
2023-11-30 | Done | Max 4 hours tasks | Reading: Ethical Guidelines for Statistical Practice | Research | ILO 6.0 | 1 | 2 | 1
2023-11-30 | Done | Max 4 hours tasks | Ethical Guidelines for Statistical Practice Exercise | Research | ILO 6.0 | 0.5 | 0.5 | 0 | LINK | Exercised information learned about ethicastatisticians and the GDPR.
2023-11-30 | Done | Max 4 hours tasks | GDPR | Research | ILO 6.0 | 2 | 2.5 | 0.5 | LINK | Introduction to the GDPR.
2023-11-30 | Done | Max 4 hours tasks | Reading: General Data Protection Regulation (2019) | Research | ILO 6.0 | 2 | 3 | 1
2023-11-30 | Done | Max 4 hours tasks | Datalab preparation (Week 2, DataLab 2) | Research | ILO 6.0 | 4 | 4 | 0 | LINK
2023-12-01 | Done | Max 4 hours tasks | Instructions on the Week9-10 challenges | Lecture | ILO 1.4 | 0.5 | 0.5 | 0
2023-12-01 | Done | Max 4 hours tasks | Meditated | Break | ILO 2.5 | 2 | 2 | - | - | Worked towards achieving my SMARTER goals.
2023-12-01 | Done | Max 4 hours tasks | Week 2, DataLab II: Dialogue | Meeting | ILO 2.5 | 1 | 1 |  | LINK (Photo)
|  |  |  | Total Hours |  | 36.75 | 45 | 8.25
Week 3
week plan: | Work with numpy; work with pandas; delve into working with real data sets
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2023-12-04 | Done | Max 4 hours tasks | Linear Algebra (Matrices Exercise) | Testing | ILO 7.0 | 1 | 2 | 1 | LINK | Exercised the basic matrices operations.
2023-12-04 | Done | Max 4 hours tasks | Linear Algebra (Matrices Exercise) | Testing | ILO 7.1 | 1 | 2 | 1 | LINK | Exercised the basic matrices operations.
2023-12-04 | Done | Max 4 hours tasks | Linear systems and Linear Regression | Research | ILO 7.0 | 1 | 2 | 1 | LINK | Got familiarised with using arrays to solve linear equations.
2023-12-04 | Done | Max 4 hours tasks | Broadcasting | Research | ILO 4.2 | 1 | 0.5 | -0.5 | LINK | Understood broadcasting in the context of using numpy .
2023-12-04 | Done | Max 4 hours tasks | Vectorising | Research | ILO 4.2 | 0.5 | 0.25 | -0.25 | LINK | Understood vectorising in the context of using numpy.
2023-12-04 | Done | Max 4 hours tasks | Datalab preparation 1 (Week 3, DataLab 1) | Testing | ILO 4.2 | 1 | 2 | 1 | LINK | Exercised writing functions using broadcasting and vectorising.
2023-12-04 | Done | Max 4 hours tasks | DataCamp: Introduction to data visualisation with Matplotlib | Study | ILO 4.2 | 4 | 4 | 0 | LINK | Got familiarised with matplolib's functionalities when it comes to different types of visualisations.
2023-12-04 | Done | Max 4 hours tasks | Matplotlib materials | Testing | ILO 4.2 | 1 | 0.1 | -0.9
2023-12-04 | Done | Max 4 hours tasks | Datalab preparation 1 (Week 3, DataLab 1) | Programming | ILO 4.2 | 0.5 | 0.5 | 0 | LINK | Practiced matplotlib visualisation techniques on a new data frame.
2023-12-05 | Done | Max 4 hours tasks | Single source of data | Programming | ILO 4.2 | 2.5 | 3 | 0.5 | LINK | Read player excel files and put them into one dataframe saved as a csv file.
2023-12-05 | Done | Max 4 hours tasks | Review session | Meeting | ILO 4.1 | 1 | 1 | 0 |  | Review session of the materal presented so far.
2023-12-05 | Done | Max 4 hours tasks | Football data exploration part I | Programming | ILO 4.2 | 4 | 4 | 0 | LINK | Cleaned up the player data.
2023-12-06 | Done | Max 4 hours tasks | Data Visualisation: NAC data | Programming | ILO 4.1 | 3 | 4 | 1 | LINK | Made a storyline using visualisations based on the NAC data
2023-12-06 | Done | Max 4 hours tasks | API connections in Python | Research | ILO 4.1 | 4 | 4 |  | LINK | Learned what API connections are and how to Python correlates with API connections.
2023-12-07 | Done | Max 4 hours tasks | Introduction to Streamlit | Programming | ILO 4.2 | 3 | 2 | 3 | LINK | Learned how to intialise and use streamlit in order to create visualisations online.
2023-12-07 | Done | Max 4 hours tasks | Making a simple calculator app using Streamlit | Programming | ILO 4.2 | 2 | 1.5 | -0.5 | LINK | Made a calculator app using python and streamlit.
2023-12-08 | Done | Max 4 hours tasks | Data Analysis: NAC 2 part 1 | Programming | ILO 4.2 | 4 | 4 | 0 | LINK | Answered the questions using visualisations (matplotlib, pandas, numpy) based on the NAC csv created on Tuesday.
2023-12-08 | Done | Max 4 hours tasks | Data Analysis: NAC 2 part 2 | Programming | ILO 4.2 | 4 | 4 | 0 | LINK | Answered the questions using visualisations (matplotlib, pandas, numpy) based on the NAC csv created on Tuesday.
|  |  |  | Total Hours |  | 38.5 | 40.85 | 2.35
Week 4
week plan: | Learn about ML; Employ my first ML model; Delve deeper into Linear Algebra concepts
Known Risks | Felt really anxious and want to take a small break.
2023-12-11 | Done | Max 4 hours tasks | Introduction to Machine Learning | Research | ILO 5.1 | 1 | 2 | 1 | PHOTO LINK | Learned about supervised and unsupervised machine learning models, and their subclassifications.
2023-12-11 | Done | Max 4 hours tasks | DataCamp: Understanding Machine Learning | Lecture | ILO 5.1 | 3 | 3 | 0 | LINK | Further comprehension into the worl of ML (supervised and unsupervised learning)
2023-12-11 | Done | Max 4 hours tasks | Feature Engineering | Programming | ILO 5.1 | 3 | 5 | 2 | LINK | Learned about different feature scaling techniques and when it's best to use which.
2023-12-11 | Done | Max 4 hours tasks | Tenets of Linear Regression | Programming | ILO 5.1 | 1 | 1 | 0 | LINK | Learned about linear regression and the process of plotting the line.
2023-12-11 | Done | Max 4 hours tasks | Correlation and Experimental Design (DataCamp: Introduction to Statistics) | Research | ILO 5.1 | 1 | 1 | 0 | LINK (SS) | Learned about correlation between variables of a dataset.
2023-12-11 | Done | Max 4 hours tasks | Classification and Regression (DataCamp: Supervised Learning with scikit-learn) | Programming | ILO 5.1 | 2 | 3 | 1 | LINK(SS) | Learned about classification models, cross-validation, linear regression, etc.
2023-12-12 | Done | Max 4 hours tasks | Introduction to Linear Regression | Research | ILO 5.1 | 1 | 4 | 3 |  | Learned about independent and dependent variables, residuals, finding the best fit, and checking the linearity assumption.
2023-12-12 | Done | Max 4 hours tasks | Application of Housing Price Prediction data | Testing | ILO 5.1 | 2 | 2.5 | 0.5 | LINK | Applied a simple and multiple linear regression model to predict housing prices.
2023-12-12 | Done | Max 4 hours tasks | Linear Regression NAC Player data | Testing | ILO 5.1 | 3 | 4 | 1 | LINK | Applied a simple and multiple linear regression model to NAC player data.
2023-12-13 | Done | Max 4 hours tasks | Introduction to Logistic Regression | Lecture | ILO 5.1 | 2 | 2.5 | 0.5 |  | Got familiar with the basics of logistic regression.
2023-12-13 | Done | Max 4 hours tasks | DataCamp: Supervised Learning with scikit-learn | Research | ILO 5.1 | 2 | 3 | 1 | LINK | Learned how to build a logistic regression model in python; learned about the ROC curve and hyperparameter tuning.
2023-12-13 | Done | Max 4 hours tasks | Logistic Regression Guided Walk-through | Testing | ILO 5.1 | 1 | 2 | 1 | LINK | Practiced implementing logistic regression models on hands-on data.
2023-12-14 | Done | Max 4 hours tasks | Evaluating Logistic Regression | Research | ILO 5.1 | 2.5 | 2.5 | 0 | LINK | Practiced calculating the evaluation metrics of ML models.
2023-12-14 | Done | Max 4 hours tasks | K Nearest Neighbours Algorithm | Research | ILO 5.1 | 3.5 | 3 | -0.5 | LINK | Practiced using the knn model on the hands-on dataset.
2023-12-14 | Done | Max 4 hours tasks | Comparison between logistic regression model and knn model | Evidencing | ILO 5.1 | 1 | 1 | 0 | LINK | Evaluated both models' performance.
2023-12-15 | Done | Max 4 hours tasks | NAC player classification | Testing | ILO 5.1 | 3 | 2.5 | -0.5 | LINK | Created two features and
|  |  |  | Total Hours |  | 32 | 42 | 10
Week 5
week plan: | Learn more about creating, tuning and evaluating ML models
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2023-12-18 | Done | Max 4 hours tasks | Understanding the Bias-Variance Tradeoff' by Scott Fortmann-Roe | Research | ILO 5.1 | 1 | 1.5 | 0.5 |  | Learned how variance and bias affect and are affected by prediction models (such as knn).
2023-12-18 | Done | Max 4 hours tasks | Reading: 'Naked Statistics' by Charles Wheelan | Study | ILO 2.5 | 4 | 3 | -1 |  | Worked towards achieving my SMARTER goals.
2023-12-18 | Done | Max 4 hours tasks | Metrics documentation | Research | ILO 5.1 | 2 | 2 | 0 |  | Learned about different evaluation metrics for ML models.
2023-12-18 | Done | Max 4 hours tasks | Cross-Validation documentation (SciKit) | Research | ILO 5.1 | 1 | 2 | 1 |  | Learned more about cross-validation.
2023-12-18 | Done | Max 4 hours tasks | Cross-Validation practice | Testing | ILO 5.1 | 3 | 3 | 0 | LINK | Exercised cross-validation on NAC logistic reg., and knn model
2023-12-18 | Done | Max 4 hours tasks | Clustering - Introduction | Research | ILO 5.1 | 1.5 | 2 | 0.5
2023-12-18 | Done | Max 4 hours tasks | DataCamp: Cluster Analysis in Python | Research | ILO 5.1 | 1 | 2 | 1 | LINK(SS) | Got introduced to types of clustering and why are useful in certain situations.
2023-12-18 | Done | Max 4 hours tasks | Types of clustering | Research | ILO 5.1 | 1.5 | 1.5 | 0 | LINK | Learned about K-means clustering, Hierarchical clustering and DBSCAN clustering.
2023-12-19 | Done | Max 4 hours tasks | Guest lecture:IBM | Workshop | ILO 2.5 | 1 | 1 | 0 |  | Insights into a Data Scient's life.
2023-12-19 | Done | Max 4 hours tasks | Worked on final template. | Programming | ILO 4.2 | 3 | 3 | 0 |  | Worked on final template deliverable.
2023-12-19 | Done | Max 4 hours tasks | DataCamp: Cluster Analysis in Python | Programming | ILO 5.1 | 3 | 3 | 0 | LINK | Further learned about K-means , hierarchical and DBSCAN clustering.
2023-12-19 | Done | Max 4 hours tasks | Clustering: Hands-on | Programming | ILO 5.1 | 3 | 2 | -1 | LINK | Practiced clustering on NAC data.
2023-12-20 | Done | Max 4 hours tasks | Introduction to Decision Trees | Programming | ILO 5.1 | 4 | 4 | 0 | LINK | Learned about decision trees (classification trees and regression trees)
2023-12-20 | Done | Max 4 hours tasks | DataCamp: Machine Learning with Tree-Based Models in Python (First module) | Programming | ILO 5.1 | 3 | 2 | -1 | LINK(SS) | Learned more about decision trees and how different criterions are use to evaluate them.
2023-12-20 | Done | Max 4 hours tasks | Decision Trees: Hands-on | Programming | ILO 5.1 | 2 | 2 | 0 | LINK | Practiced the different criterion and calculated their computation duration.
2023-12-21 | Done | Max 4 hours tasks | Buffer day | Planning | ILO 2.5 | 4 | 4 | 0 |  | Caught up with other work.
2023-12-22 | Done | Max 4 hours tasks | Reading: 'Naked Statistics' by Charles Wheelan | Study | ILO 2.5 | 2 | 3 | 1 |  | Worked towards achieving my SMARTER goals.
2023-12-22 | Done | Max 4 hours tasks | Meditated | Break | ILO 2.5 | 1 | 1 | - | - | Worked towards achieving my SMARTER goals.
2023-12-22 | Done | Max 4 hours tasks | Mandatory day off | Break | - | - | - | - | - | -
|  |  |  | Total Hours |  | 41 | 42 | 1
Week 6
week plan: | Work on final projects; make a plan for the final report; finish learning about the ML models
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-01-08 | Done | Max 4 hours tasks | DataCamp: Machine Learning with Tree-Based Models in Python (Second module) | Lecture | ILO 4.2 | 1 | 1 | 0 | LINK | Got introduced to the bagging and random forest classifiers.
2024-01-08 | Done | Max 4 hours tasks | DataCamp: Machine Learning with Tree-Based Models in Python (Third module) | Lecture | ILO 4.2 | 1 | 1 | 0 | LINK | Got introduced to the bias-variance tradeoff.
2024-01-08 | Done | Max 4 hours tasks | Worked on final template. | Programming | ILO 4.2 | 4 | 4 | 0 |  | Worked on final template deliverable.
2024-01-08 | Done | Max 4 hours tasks | Worked on final report. | Programming | ILO 4.2 | 1 | 1.5 | 0.5 |  | Worked on final report deliverable.
2024-01-08 | Done | Max 4 hours tasks | Random Forests | Programming | ILO 4.3 | 4 | 4 | 0 | LINK | Implemented random forests on the breast cancer dataset.
2024-01-09 | Done | Max 4 hours tasks | Application on NAC Dataset | Programming | ILO 4.2 | 4 | 4 | 0 | LINK | Applied random forest model on NAC dataset.
2024-01-09 | Done | Max 4 hours tasks | NAC Q&A | Research | ILO 4.2 | 3 | 3 | 0 |  | Asked a NAC representative questions about the final projects and listened to classmates' presentations.
2024-01-10 | Done | Max 4 hours tasks | Bagging and Boosting | Programming | ILO 4.2 | 2.5 | 2.5 | 0 |  | Got introduced to bagging and boosting, and their use for machine learning algorithms.
2024-01-10 | Done | Max 4 hours tasks | DataCamp: Machine Learning with Tree-Based Models in Python (Fourth module) | Programming | ILO 4.2 | 2 | 2 | 0 | LINK
2024-01-10 | Done | Max 4 hours tasks | Gradient Boosting Hands-on | Programming | ILO 4.1 | 2 | 2 | 0 | LINK | Exercised gradient boosting on wisconsin breast cancer dataset.
2024-01-10 | Done | Max 4 hours tasks | Worked on final template. | Programming | ILO 4.2 | 2 | 3 | 1 |  | Worked on final template deliverable.
2024-01-11 | Done | Max 4 hours tasks | Introduction to Hyperparameters | Programming | ILO 5.1 | 2.5 | 2.5 | 0 | LINK | Got introduced to hyperparameters in the context of machine learning.
2024-01-11 | Done | Max 4 hours tasks | Hyperparameter tuning youtube tutorial | Programming | ILO 5.2 | 0.5 | 0.5 | 0 | LINK | Followed a youtube tutorial on hyperparameter tuning.
2024-01-11 | Done | Max 4 hours tasks | DataCamp: Machine Learning with Tree-Based Models in Python (Final module) | Programming | ILO 5.1 | 2 | 2 | 0 | LINK
2024-01-11 | Done | Max 4 hours tasks | Hyperparameter tuning - Hands-on | Programming | ILO 5.1 | 2.5 | 2.5 | 0 | LINK | Exercised hyperparameter tuning on the iris dataset.
2024-01-12 | Done | Max 4 hours tasks | Consolidating ML Algorithms for NAC Dataset | Programming | ILO 4.2 | 4 | 4 | 0 | LINK | Put all of the exercised models into one jupyter notebook.
2024-01-12 | Done | Max 4 hours tasks | Worked on final template. | Programming | ILO 4.2 | 2 | 2 | 0 |  | Worked on final template deliverable.
2024-01-12 | Done | Max 4 hours tasks | Worked on final report. | Programming | ILO 4.2 | 3 | 3 | 0 |  | Worked on final report deliverable.
|  |  |  | Total Hours |  | 43 | 44.5 | 1.5
Week 7
week plan: | Work on final projects; Introduction to calculus
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-01-15 | Done | Max 4 hours tasks | Introduction to PCA - Principal Component Analysis and Dimensionality Reduction | Programming | ILO 5.1 | 2 | 2 | 0 | LINK | Got introduced to PCA, understood its importance and step-by-step application.
2024-01-15 | Done | Max 4 hours tasks | Worked on final template. | Programming | ILO 4.2 | 3 | 3 | 0 |  | Worked on final template deliverable.
2024-01-15 | Done | Max 4 hours tasks | DataCamp: Dimensionality Reduction in Python | Programming | ILO 5.1 | 4 | 4 | 0 | LINK | Further comprehension into principal component analysis.
2024-01-16 | Done | Max 4 hours tasks | Improving Performance metrics | Research | ILO 5.1 | 2 | 2 | 0 |  | Learned how to optimize your model run time and model accuracy
2024-01-16 | Done | Max 4 hours tasks | Hands-on Final model | Programming | ILO 5.1 | 4 | 4 | 0 | LINK | Practiced model optimisation using L1 and L2 regularisation.
2024-01-16 | Done | Max 4 hours tasks | Worked on final report. | Programming | ILO 4.2 | 3 | 3 | 0 |  | Worked on final report deliverable.
2024-01-17 | Done | Max 4 hours tasks | Exploring Calculus: Derivatives, Limits, and Applications | Research | ILO 7.0 | 2 | 2.5 | 0.5 |  | Learned about derivatives and limits.
2024-01-17 | Done | Max 4 hours tasks | Differential calculus course | Testing | ILO 7.0 | 4 | 4 | 0 | LINK | Practised working with limits and derivatives.
2024-01-18 | Done | Max 4 hours tasks | Introduction to Multivariable Calculus | Research | ILO 7.0 | 1.5 | 2 | 0.5 |  | Learned about partial derivatives and gradients.
2024-01-18 | Done | Max 4 hours tasks | Multivariable calculus assignments | Research | ILO 7.0 | 2 | 3 | 1 | LINK | Practiced partial derivatives and gradients.
2024-01-18 | Done | Max 4 hours tasks | Multivariable calculus assignments | Programming | ILO 7.0 | 2 | 2 | 0 | LINK | Practiced partial derivatives and gradients python.
2024-01-19 | Done | Max 4 hours tasks | Symbolic Computation with SymPy | Programming | ILO 7.0 | 3 | 3 | 0 |  | Got familiar with the SymPy library.
2024-01-19 | Done | Max 4 hours tasks | DataLab Tasks | Programming | ILO 7.0 | 4 | 4 | 0 | LINK | Practiced using the SymPy library with derivatives, limits and Taylor series'.
2024-01-19 | Done | Max 4 hours tasks | Worked on final template. | Programming | ILO 4.2 | 3 | 3 | 0 |  | Worked on final template deliverable.
|  |  |  | Total Hours |  | 39.5 | 41.5 | 2
Week 8
week plan: | Finish with everything
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-01-22 | Done | Max 4 hours tasks | Gradient Descent Optimization Algorithm | Programming | ILO 7.0 | 0.5 | 0.5 | 0 |  | Got introduced to gradient descent.
2024-01-22 | Done | Max 4 hours tasks | Implementing a Linear Regression Model Using Gradient Descent | Programming | ILO 7.0 | 0.5 | 1 | 0.5 |  | Revised how to implement a linear regression model using a single variable.
2024-01-22 | Done | Max 4 hours tasks | Train the Model with Gradient Descent | Programming | ILO 7.0 | 1 | 1 | 0 |  | Learned how to implement a linear regression model using the gradient descent algorithm and learned about the cost function.
2024-01-22 | Done | Max 4 hours tasks | Assignments | Programming | ILO 7.0 | 2 | 4 | 2 |  | Praciced implementing the information learned today.
2024-01-22 | Done | Max 4 hours tasks | Worked on final template. | Programming | ILO 4.2 | 3 | 3 | 0 |  | Worked on final template deliverable.
2024-01-22 | Done | Max 4 hours tasks | Worked on final report. | Programming | ILO 4.2 | 3 | 3 | 0 |  | Worked on final report deliverable.
2024-01-23 | Done | Max 4 hours tasks | DataLab Tasks | Programming | ILO 5.1 | 4 | 4 | 0 |  | Got familiar with the mathematical equations for linear regression using multiple features implemented by the gradient descent algorithm.
2024-01-24 | Done | Max 4 hours tasks | Worked on final template. | Programming | ILO 4.2 | 3 | 3 | 0 |  | Completed the linear algebra section.
2024-01-24 | Done | Max 4 hours tasks | Worked on final report. | Programming | ILO 4.3 | 3 | 3 | 0 |  | Completed EDA section and put images.
2024-01-25 | Done | Max 4 hours tasks | Worked on final report. | Programming | ILO 4.2 | 3 | 3 | 0 |  | Wrote recomandations.
2024-01-25 | Done | Max 4 hours tasks | Worked on final template. | Programming | ILO 4.3 | 3 | 3 | 0 |  | Added markdown comments to explain every visualisation.
2024-01-26 | Done | Max 4 hours tasks | Finished deliverable 1 | Programming | ILO 5.1 | 4 | 4 | 0 | LINK | Worked on final details such as adding comments, putting titles on visualisations, and completing the improving the model section.
2024-01-26 | Done | Max 4 hours tasks | Finished deliverable 2 | Programming | ILO 5.1 | 4 | 4 | 0 | LINK | Wrote conclusion.
|  |  |  | Total Hours |  | 34 | 36.5 | 2.5
|  |  |  | Total hours this block |  | 303.91 | 332.76 | 28.85

## Drop-downs
Task Status | Task Type | ILO selection
- | - | -
Planned | Design | ILO 1.4
Unplanned | Meeting | ILO 2.5
Blocked | Programming | ILO 3.1
In-Progress | Research | ILO 4.1
Done | Testing | ILO 4.2
Delayed | Workshop | ILO 5.1
Cancelled | Planning | ILO 6.0
| Evidencing | ILO 7.0
Debugging
Lecture
Study
Unplanned
Distraction
Break