## Worklog_Tasks&Times
Date | Task | Description/Planning | Est Hours | Actual Hours | Diff | Evidence link | Task reflection / notes
Week 9
2024-01-29 | Max 4 hour task | Got familiar with the Choreography app | 2 | 1 | -1 |  | Briefly understood how to work with the app for the robots.
2024-01-29 | Max 4 hour task | Got familiar with NAO | 2 | 2 | 0 |  | Briefly understood how the virtual robot works.
2024-01-30 | Max 4 hour task | Worked on the project | 3 | 3 | 0 |  | Made NAO a service robot to be used on the open day.
2024-01-31 | Max 4 hour task | Discussed with the team and drew up a plan | 2 | 3 | 1 |  | Briefly understood how the robot works. Unfortunately we could not make Pepper work for our team (Kept getting an error message)
2024-01-31 | Max 4 hour task | Working with the robot | 3 | 4 | 1 |  | Agreed on what we want to do with the robots with a focus on NAO because Pepper wasn't working
2024-02-01 | Max 4 hour task | Worked on the project | 3 | 3 | 0 |  | Worked with the programme.
2024-01-02 | Max 4 hour task | Working with the virtual robot | 2 | 3.5 | 1.5 |  | 3.5
2024-02-02 | Max 4 hour task | Reading some material on the robot and tryin it out on the robot | 2.5 | 3 | 0.5 |  | 4
|  |  | 19.5 | 22.5 | 3
Week 10
2024-02-05 | Max 4 hour task | Meeting with the team and trying to combine our ideas and work together. | 4 | 5 | 1 |  | Decided to change our original plan for the robot.
2024-02-06 | Max 4 hour task | Worked on the project | 3 | 2 | -1
2024-02-07 | Max 4 hour task | Worked on the project | 1 | 1 | 0
2024-02-08 | Max 4 hour task | Worked on the project | 1 | 1 | 0
|  |  | 9 | 9 | 0
Total hours: |  |  | 28.5 | 31.5 | 3